## Read Me
TRUE | START
FALSE | END
FALSE

## W90 MP
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 7.1 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 2.5 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 2.5 | 18 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 2.5 | 18 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 7.1 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 6 | 18 | 50% | 1 | 3 | FALSE | FALSE | START
7 | Move MP from setback to Main Hook position | 2 | 6 | 18 | 50% | 1 | 3 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 2.5 | 18 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2.5 | 18 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2.5 | 18 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 6 | 18 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## W90 Jacket
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to Wind Farm | Given by distance | 6 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival Wind Farm, positioning with barge and preperations for lift. | 2 | 2.5 | 18 | 20% | 0.4 | 2.4 | FALSE | FALSE | START
3 | Jacket is upended (if required) and lifted from the transport barge to the installation position using main crane | 3 | 2.5 | 18 | 20% | 0.6 | 3.6 | FALSE | FALSE | FALSE
4 | Jacket is carefully lowered to the seabed and positioned accurately using GPS and survey systems. | 6 | 2.5 | 18 | 20% | 1.2 | 7.2 | FALSE | FALSE | FALSE
5 | Steel piles are driven through the jacket legs into the seabed using hydraulic hammers to secure the structure. | 14 | 2.5 | 18 | 20% | 2.8 | 16.8 | FALSE | FALSE | FALSE
6 | Grout is injected to lock the piles and jacket legs together for structural integrity. | 6 | 2.5 | 18 | 20% | 1.2 | 7.2 | FALSE | FALSE | FALSE
7 | Final checks and adjustments to ensure the jacket is level and in the correct position. | 4 | 6 | 18 | 20% | 0.8 | 4.8 | FALSE | FALSE | END
8 | Vessel repositions or prepares for the next jacket installation. | 2 | 6 | 18 | 20% | 0.4 | 2.4 | TRUE | FALSE | FALSE

## W90 WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation | Parallell 1 | Parallell 2
1 | Position W90 to engage loading | 1 | 6 | 18 | 0% | 0 | 1 | FALSE | FALSE | FALSE | FALSE | FALSE
2 | Move barge alongside W90 starboard. Attach to W90 | 1 | 2.5 | 18 | 0% | 0 | 1 | FALSE | START | FALSE | TRUE | FALSE
3 | Connect W90 SDC and lift main TT 1 and secure on board | 1.5 | 2.5 | 18 | 20% | 0.3 | 1.8 | FALSE | FALSE | FALSE | TRUE | FALSE
4 | Lift main section 2, Bolt scrion 1 & 2 together | 2.5 | 2.5 | 18 | 20% | 0.5 | 3 | FALSE | FALSE | FALSE | TRUE | FALSE
5 | Lift and bolt section 3. Connect W90 SDC and lift TT main section 4 to W90 catwalk | 3 | 2.5 | 18 | 20% | 0.6 | 3.6 | FALSE | FALSE | FALSE | TRUE | FALSE
6 | Bolt TT section 3 and 4 together in AP1 and seafasten in setback | 2.5 | 2.5 | 18 | 20% | 0.5 | 3 | FALSE | FALSE | FALSE | TRUE | FALSE
7 | Transport barge for loading on port side of W90. Moore to W90. | 1 | 2.5 | 18 | 20% | 0.2 | 1.2 | FALSE | FALSE | FALSE | FALSE | TRUE
8 | PDC lift 8 lower TT sections onto W90 to skid landing area port side. Skid and seafasten all lower TT tubes in W90 deck storage area | 1.125 | 2.5 | 18 | 20% | 0.225 | 1.35 | FALSE | FALSE | FALSE | FALSE | TRUE
9 | 2 transport barges loaded with 8 nacelles (30x10x10m, ea1400t) ready. Move Nacelle barge alongside W90 port side (2 tugs). Moore to W90. | 1 | 2.5 | 18 | 20% | 0.2 | 1.2 | FALSE | FALSE | FALSE | FALSE | TRUE
10 | PDC lift 8 Nacelles onto W90 to skid landing area port side. Skid and seafasten all Nacelles in W90 deck storage area. | 3.5 | 2.5 | 18 | 20% | 0.7 | 4.2 | FALSE | FALSE | FALSE | FALSE | TRUE
11 | 4 Transport barges with 24 rotor blades (for 8WTG's) Ready in sheltered area. Offload from barges and store 24 rotor blades onboard W90 blade rack. | 5.5 | 2.5 | 18 | 20% | 1.1 | 6.6 | FALSE | END | FALSE | FALSE | TRUE
12 | Transit to project site | NA | 2.5 | 18 | 0% | 0 | 0 | TRUE | FALSE | FALSE | FALSE | FALSE
13 | Position W90 over foundation. Lift main TT up and transverse over top of lower TT | 1 | 6 | 18 | 30% | 0.3 | 1.3 | FALSE | FALSE | START | FALSE | FALSE
14 | Position and bolt up lower and main TT in MAP | 1.5 | 6 | 18 | 40% | 0.6 | 2.1 | FALSE | FALSE | FALSE | FALSE | FALSE
15 | Move TT gripping tool to SAP | 0.3 | 6 | 18 | 10% | 0.03 | 0.33 | FALSE | FALSE | FALSE | FALSE | FALSE
16 | Main hoist connect & install nacelle yoke, elevator to TT. Position and bolt nacelle to top of TT | 4 | 6 | 18 | 0% | 0 | 4 | FALSE | FALSE | FALSE | FALSE | FALSE
17 | Lift TT with nacelle, move forward to blade inst. Position. Install blade 1 to hub, bolt up | 2.8 | 6 | 18 | 30% | 0.84 | 3.64 | FALSE | FALSE | FALSE | FALSE | FALSE
18 | Rotate hub 120 deg. Install blade 2 to hub, bolt up | 2.8 | 6 | 18 | 30% | 0.84 | 3.64 | FALSE | FALSE | FALSE | FALSE | FALSE
19 | Rotate hub 120 deg. Install blade 3 to hub, bolt up | 2.8 | 6 | 18 | 30% | 0.84 | 3.64 | FALSE | FALSE | FALSE | FALSE | FALSE
20 | Align W90 and WTG for connection to TP-BF foundation. Lower WTG onto TP- foundation, bolt up. Disconnect from WTG | 2.5 | 4 | 18 | 30% | 0.75 | 3.25 | FALSE | FALSE | FALSE | FALSE | FALSE
21 | Move W90 0.5NM to next location | 0.5 | 6 | 18 | 0% | 0 | 0.5 | FALSE | FALSE | END | FALSE | FALSE
22 | Transit to loading location | NA | 6 | 18 | 0% | 0 | 0 | TRUE | FALSE | FALSE | FALSE | FALSE

## JUV MP
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 1 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 1.5 | 11 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 1 | 11 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 2.5 | 14 | 50% | 1 | 3 | FALSE | FALSE | END
7 | Move MP from DECK to Main Hook position | 6 | 1.5 | 11 | 50% | 3 | 9 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 1.5 | 11 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2 | 11 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2 | 11 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 4 | 14 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## JUV Jacket
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival Wind Farm, positioning , pre load and jack up. Position barge. | 4 | 1.5 | 14 | 20% | 0.8 | 4.8 | FALSE | FALSE | START
3 | Jacket is upended (if required) and lifted from the transport barge to the installation position using main crane | 4 | 1.5 | 11 | 20% | 0.8 | 4.8 | FALSE | FALSE | FALSE
4 | Jacket is carefully lowered to the seabed and positioned accurately using GPS and survey systems. | 6 | 2.5 | 11 | 20% | 1.2 | 7.2 | FALSE | FALSE | FALSE
5 | Steel piles are driven through the jacket legs into the seabed using hydraulic hammers to secure the structure. | 16 | 2.5 | 11 | 20% | 3.2 | 19.2 | FALSE | FALSE | FALSE
6 | Grout is injected to lock the piles and jacket legs together for structural integrity. | 8 | 2.5 | 11 | 20% | 1.6 | 9.6 | FALSE | FALSE | FALSE
7 | Final checks and adjustments to ensure the jacket is level and in the correct position. | 4 | 4 | 14 | 20% | 0.8 | 4.8 | FALSE | FALSE | END
8 | Vessel jack down and prepares for the next jacket installation location. | 3 | 1.5 | 18 | 20% | 0.6 | 3.6 | TRUE | FALSE | FALSE

## JUV WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit into port | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
2 | port entry to load-out quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
3 | jack-up at port / quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
4 | preparatory works (e.g. gangway secured, backloading Owner, etc.) | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
5 | handover main crane from Owner to WTG OEM | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
6 | backloading WTG items incl. TP-cover | 2 | NA | 14 | 60% | 3 | 5 | FALSE | FALSE | FALSE
7 | Loading of WTG tower | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | START | FALSE
8 | Loading of WTG nacelle | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
9 | Loading of blades for ( Time per blade x Number of turbines carried) | 1.75 | NA | 8.25 | 58.82% | 2.5 | 4.25 | FALSE | FALSE | FALSE
10 | Loading of auxiliary equipment of WTG-OEM | 2 | NA | 12 | 55.56% | 2.5 | 4.5 | FALSE | END | FALSE
11 | handover main crane from WTG OEM to Owner | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
12 | Finish load-out operations and prepare for sailing jack-down at port | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
13 | port exit | 0.5 | NA | NA | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
14 | Transit to Project location | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
15 | DP trials before entering Dreekant OWF borders | 1 | 3 | NA | 50% | 1 | 2 | FALSE | FALSE | FALSE
16 | pre-loading and jack-up to working height | 2 | 2 | 13.5 | 66.67% | 4 | 6 | FALSE | FALSE | FALSE
17 | handover main crane from Owner to WTG OEM | 1 | 2 | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
18 | preparation of TP and TP-cover removal | 2 | NA | 12 | 42.86% | 1.5 | 3.5 | FALSE | FALSE | FALSE
19 | prepare for tower lifting | 3 | NA | 12 | 40% | 2 | 5 | FALSE | FALSE | START
20 | installation of tower (safe to safe) | 1 | NA | 10.5 | 83.33% | 5 | 6 | FALSE | FALSE | FALSE
21 | de-rigging tower | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
22 | prepare for nacelle lifting | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
23 | installation of nacelle (safe to safe) | 2.5 | NA | 10.5 | 61.54% | 4 | 6.5 | FALSE | FALSE | FALSE
24 | de-rigging nacelle | 1 | NA | 12 | 50% | 1 | 2 | FALSE | FALSE | FALSE
25 | prepare for blade lifting | 1 | NA | 10.5 | 50% | 1 | 2 | FALSE | FALSE | FALSE
26 | installation of blade 1 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
27 | installation of blade 2 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
28 | installation of blade 3 (per blade & safe to safe) | 2.5 | NA | 8.25 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
29 | de-rigging blades | 3 | NA | 10.5 | 50% | 3 | 6 | FALSE | FALSE | FALSE
30 | WTG completion works | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
31 | handover main crane from WTG OEM to Owner | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
32 | preparation works before jack-down | 1 | NA | 13.5 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
33 | jack-down at location | 0.5 | NA | 13.5 | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
34 | Relocate to next asset | 0.5 | 3 | NA | 50% | 0.5 | 1 | FALSE | FALSE | END

## FIV MP
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to sheltered area or Yard | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival and mooring | 1 | 1 | 18 | 50% | 0.5 | 1.5 | FALSE | START | FALSE
3 | Loading each Monopile | 8 | 1.5 | 11 | 50% | 4 | 12 | FALSE | FALSE | FALSE
4 | Sea-fastening and departure | 3 | 1 | 11 | 50% | 1.5 | 4.5 | FALSE | END | FALSE
5 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
6 | Arrival Wind Farm, positioning and preperations | 2 | 2.5 | 14 | 50% | 1 | 3 | FALSE | FALSE | END
7 | Move MP from DECK to Main Hook position | 6 | 1.5 | 11 | 50% | 3 | 9 | FALSE | FALSE | FALSE
8 | Monopile is lowered to the seabed and positioned accurately. | 4 | 1.5 | 11 | 50% | 2 | 6 | FALSE | FALSE | FALSE
9 | Monopile is driven into the seabed using a vibro-hammer (initial) and then a hydraulic impact hammer (main driving). (Ad 10 horus if drilling) | 10 | 2 | 11 | 50% | 5 | 15 | FALSE | FALSE | FALSE
10 | Check and Verifications | 2 | 2 | 11 | 50% | 1 | 3 | FALSE | FALSE | FALSE
11 | Move to next location | 1 | 4 | 14 | 50% | 0.5 | 1.5 | FALSE | FALSE | END

## FIV Jacket
N | Description - MP Piling (non drilling) | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit to Wind Farm | Given by distance | 4 | 18 | NA | NA | Given by distance | TRUE | FALSE | FALSE
2 | Arrival Wind Farm, positioning with barge and preperations for lift. | 3 | 2.5 | 14 | 20% | 0.6 | 3.6 | FALSE | FALSE | START
3 | Jacket is upended (if required) and lifted from the transport barge to the installation position using main crane | 4 | 1.5 | 11 | 20% | 0.8 | 4.8 | FALSE | FALSE | FALSE
4 | Jacket is carefully lowered to the seabed and positioned accurately using GPS and survey systems. | 6 | 1.5 | 11 | 20% | 1.2 | 7.2 | FALSE | FALSE | FALSE
5 | Steel piles are driven through the jacket legs into the seabed using hydraulic hammers to secure the structure. | 14 | 2 | 11 | 20% | 2.8 | 16.8 | FALSE | FALSE | FALSE
6 | Grout is injected to lock the piles and jacket legs together for structural integrity. | 6 | 2 | 11 | 20% | 1.2 | 7.2 | FALSE | FALSE | FALSE
7 | Final checks and adjustments to ensure the jacket is level and in the correct position. | 4 | 4 | 14 | 20% | 0.8 | 4.8 | FALSE | FALSE | END
8 | Vessel repositions or prepares for the next jacket installation. | 2 | 4 | 18 | 20% | 0.4 | 2.4 | TRUE | FALSE | FALSE

## FIV WTG
N | Description | Seq Dur (hrs) | Oplim Waves (m) | Oplim Wind (m/s) | Tc (hrs) % | Tc (hrs) | Tr (hrs) | Transit | Loading | Installation
1 | Transit into port | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
2 | port entry to load-out quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
3 | jmooring port / quay | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
4 | preparatory works (e.g. gangway secured, backloading Owner, etc.) | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
5 | handover main crane from Owner to WTG OEM | 0.75 | NA | NA | 57.14% | 1 | 1.75 | FALSE | FALSE | FALSE
6 | backloading WTG items incl. TP-cover | 2 | NA | 14 | 60% | 3 | 5 | FALSE | FALSE | FALSE
7 | Loading of WTG tower | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | START | FALSE
8 | Loading of WTG nacelle | 2.5 | NA | 10.5 | 60% | 3.75 | 6.25 | FALSE | FALSE | FALSE
9 | Loading of blades for ( Time per blade x Number of turbines carried) | 1.75 | NA | 8.25 | 58.82% | 2.5 | 4.25 | FALSE | FALSE | FALSE
10 | Loading of auxiliary equipment of WTG-OEM | 2 | NA | 12 | 55.56% | 2.5 | 4.5 | FALSE | END | FALSE
11 | handover main crane from WTG OEM to Owner | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
12 | Finish load-out operations and prepare for sailing jack-down at port | 1 | NA | NA | 60% | 1.5 | 2.5 | FALSE | FALSE | FALSE
13 | port exit | 0.5 | NA | NA | 50% | 0.5 | 1 | FALSE | FALSE | FALSE
14 | Transit to Project location | Transit | NA | NA |  |  |  | TRUE | FALSE | FALSE
15 | DP positioning on foundation | 1 | 2.5 | 15 | 50% | 1 | 2 | FALSE | FALSE | START
16 | TP / interface inspection | 1 | 2 | 15 | 80% | 4 | 5 | FALSE | FALSE | FALSE
17 | Lift tower section 1 | 1 | 2 | 14 | 66.67% | 2 | 3 | FALSE | FALSE | FALSE
18 | Set‑down & bolt tower section 1 | 1.5 | 1.5 | 12 | 50% | 1.5 | 3 | FALSE | FALSE | FALSE
19 | Lift/set tower section 2 | 3 | 1.5 | 12 | 40% | 2 | 5 | FALSE | FALSE | FALSE
20 | Lift/set tower section 3 (if any) | 3 | 1.5 | 12 | 62.5% | 5 | 8 | FALSE | FALSE | FALSE
21 | Lift nacelle from deck | 1.5 | 1.5 | 11 | 40% | 1 | 2.5 | FALSE | FALSE | FALSE
22 | Nacelle overboard & set‑down | 2 | 1.25 | 10 | 33.33% | 1 | 3 | FALSE | FALSE | FALSE
23 | Lift blade 1 | 1 | 1.5 | 11 | 80% | 4 | 5 | FALSE | FALSE | FALSE
24 | Blade 1 hub mating & bolting | 2 | 1.5 | 10 | 33.33% | 1 | 3 | FALSE | FALSE | FALSE
25 | Blade 2 install | 4 | 1.25 | 10 | 20% | 1 | 5 | FALSE | FALSE | FALSE
26 | Blade 3 install | 4 | 1.25 | 10 | 48.39% | 3.75 | 7.75 | FALSE | FALSE | FALSE
27 | Final bolting & torqueing | 2 | 2 | 15 | 65.22% | 3.75 | 5.75 | FALSE | FALSE | FALSE
28 | Mechanical completion checks | 2 | 2.5 | 18 | 65.22% | 3.75 | 5.75 | FALSE | FALSE | FALSE
29 | Clear turbine & move‑off to next location | 3 | 3 | 18 | 50% | 3 | 6 | FALSE | FALSE | END